## Sprint1 Week1
|  | Week 1 |  | Sprint 1 - Active Tickets
18
17
Effort Scale |  |  |  | 16 | [8 empty] | Team Members
Nº | Average time |  |  | 15 | [8 empty] | DM | Daniel Machado
1 | 1 hour |  |  | 14 | [8 empty] | DL | Daniel Lima
2 | 2 hours |  |  | 13 | [8 empty] | IC | Inês Clavel
3 | 4 hours |  |  | 12 | [8 empty] | TL | Thales Lemos
5 | 1 day |  |  | 11 | [8 empty] | ALL | ALL
8 | 2 days |  |  | 10
12 | 3 days |  |  | 9
8
7
6
5
4
|  | Lingua | 8 | 3 | [7 empty] | ALL
|  | Aspell | 12 | 2 | [7 empty] | ALL
|  | Lucene | 12 | 1 | [7 empty] | ALL
[5 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday

## Sprint1 Week2
|  | Week 2 |  | Sprint 1 - Active Tickets
18
17
16
15
14
13
Effort Scale |  | SD | 1 | 12 | [9 empty] | Team Members
Nº | Average time | Glossary | 5 | 11 | [7 empty] | IC |  | DM | Daniel Machado
1 | 1 hour | Report | 8 | 10 | [7 empty] | IC | DL | DL | Daniel Lima
2 | 2 hours | CD | 2 | 9 | [7 empty] | ALL |  | IC | Inês Clavel
3 | 4 hours | DM | 2 | 8 | [7 empty] | ALL |  | TL | Thales Lemos
5 | 1 day | SSD | 5 | 7 | [7 empty] | ALL |  | ALL | ALL
8 | 2 days | Architecture | 8 | 6 | [7 empty] | ALL
12 | 3 days | Prototype | 8 | 5 | [7 empty] | ALL
|  | POC | 12 | 4 | [7 empty] | DM
|  | Lingua | 8 | 3 | [7 empty] | ALL
|  | Aspell | 12 | 2 | [7 empty] | ALL
|  | Lucene | 12 | 1 | [7 empty] | ALL
[5 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday

## Sprint2 Week1
|  | Week 1 |  | Sprint 1 - Active Tickets
18
|  | PDS Evaluation | 3 | 17
Effort Scale |  | Documentation | 12 | 16 | [7 empty] | Team Members
Nº | Average time | LanguageDet. | 8 | 15 | [7 empty] | DM | Daniel Machado
1 | 1 hour | Interfaces | 8 | 14 | [7 empty] | DL | Daniel Lima
2 | 2 hours | Business Val. | 5 | 13 | [7 empty] | IC | Inês Clavel
3 | 4 hours | WebSecurityC. | 3 | 12 | [7 empty] | TL | Thales Lemos
5 | 1 day | Domain Serv. | 5 | 11 | [7 empty] | ALL | ALL
8 | 2 days | Controllers | 3 | 10
12 | 3 days | Services | 3 | 9
|  | Value Objects | 2 | 8
|  | JPA | 3 | 7
|  | DTO | 3 | 6
|  | Assemblers | 5 | 5
|  | Blacklist | 5 | 4
|  | Factorys | 3 | 3
|  | Category | 3 | 2
|  | Task | 5 | 1
[5 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday

## Sprint2 Week2
|  | Week 2 |  | Sprint 2 - Active Tickets
Effort Scale |  | Gen. FindAll SD | 2 | 35 | [7 empty] | DM |  | Team Members
Nº | Average time | Gen. Delete SD | 2 | 34 | [7 empty] | TL |  | DM | Daniel Machado
1 | 1 hour | Gen. Create SD | 2 | 33 | [7 empty] | TL |  | DL | Daniel Lima
2 | 2 hours | Architecture D. | 2 | 32 | [7 empty] | DM |  | IC | Inês Clavel
3 | 4 hours | Status Diagram | 1 | 31 | [7 empty] | DM |  | TL | Thales Lemos
5 | 1 day | Class Diagram | 2 | 30 | [7 empty] | DM | IC | ALL | ALL
8 | 2 days | Domain Model | 2 | 29 | [7 empty] | DM
12 | 3 days | Report | 5 | 28 | [7 empty] | IC
|  | Threads Docs | 5 | 27 | [7 empty] | DL | DM
|  | Task Docs | 8 | 26 | [7 empty] | DL
|  | Task Docs | 8 | 25 | [7 empty] | DM
|  | Category Docs | 8 | 24 | [7 empty] | TL
|  | Blacklist Docs | 8 | 23 | [7 empty] | IC
|  | Threads Tests | 12 | 22 | [7 empty] | DL
|  | Task Tests | 8 | 21 | [7 empty] | DL
|  | Task Tests | 8 | 20 | [7 empty] | DM
|  | Category Tests | 8 | 19 | [7 empty] | TL
|  | Blacklist Tests | 8 | 18 | [7 empty] | IC
|  | Restructure | 8 | 17 | [7 empty] | ALL
|  | Glossary | 5 | 16 | [7 empty] | IC | DL
|  | US5 -UC5 | 2 | 15 | [7 empty] | DL
|  | US5 -UC4 | 2 | 14 | [7 empty] | DL
|  | US4 -UC3 | 5 | 13 | [7 empty] | DM
|  | US4 -UC2 | 12 | 12 | [7 empty] | DL
|  | US4 -UC1 | 12 | 11 | [7 empty] | DM
|  | US3 -UC3 | 5 | 10 | [7 empty] | IC
|  | US3 -UC2 | 5 | 9 | [7 empty] | IC
|  | US3 -UC1 | 5 | 8 | [7 empty] | IC
|  | US2 - UC6 | 12 | 7 | [7 empty] | DM
|  | US2 - UC5 | 1 | 6 | [7 empty] | TL
|  | US2 - UC4 | 2 | 5 | [7 empty] | TL
|  | US2 - UC3 | 2 | 4 | [7 empty] | TL
|  | US2 - UC2 | 2 | 3 | [7 empty] | TL
|  | US2 - UC1 | 2 | 2 | [7 empty] | TL
|  | US1 - UC4 | 2 | 1 | [7 empty] | IC
[5 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday

## Sprint3 Week1
|  | Week 1 |  | Sprint 3 - Active Tickets
8
Effort Scale |  | Documentation | 12 | 7 | [7 empty] | All |  | Team Members
Nº | Average time | US1 to 5 - JS | 8 | 6 | [7 empty] | TL |  | DM | Daniel Machado
1 | 1 hour | US1 to 5 - HTML | 8 | 5 | [7 empty] | IC |  | DL | Daniel Lima
2 | 2 hours | Refactor/corrections | 12 | 4 | [7 empty] | DM | TL | IC | Inês Clavel
3 | 4 hours | Refactor/arrangements | 12 | 3 | [7 empty] | All |  | TL | Thales Lemos
5 | 1 day | SpringSecurity | 8 | 2 |  |  |  | Study |  |  |  | DL |  | ALL | ALL
8 | 2 days | Bootstrap | 8 | 1 |  |  |  | Study |  |  |  | IC
12 | 3 days |  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday

## Sprint3 Week2
|  | Week 2 |  | Sprint 3 - Active Tickets
|  | Frontend Tests | 2 | 15 | [7 empty] | TL | IC
Effort Scale |  | Layerd Diagram | 5 | 14 | [7 empty] | ALL |  | Team Members
Nº | Average time | US 3 Doc Update | 3 | 13 | [7 empty] | DL |  | DM | Daniel Machado
1 | 1 hour | US 2 Doc Update | 3 | 12 | [7 empty] | DM |  | DL | Daniel Lima
2 | 2 hours | Domain Model | 5 | 11 | [7 empty] | IC |  | IC | Inês Clavel
3 | 4 hours | Class Diagram | 5 | 10 | [7 empty] | ALL |  | TL | Thales Lemos
5 | 1 day | Report | 5 | 9 | [7 empty] | IC |  | ALL | All members
8 | 2 days | Complex unit tests | 8 | 8 | [7 empty] | DM | DL
12 | 3 days | JavaDoc | 5 | 7 | [7 empty] | DL
|  | Frontend Glossary | 2 | 6 | [7 empty] | IC
|  | Backend Gloss. update | 2 | 5 | [7 empty] | TL
|  | US1 to 5 - JS | 8 | 4 | [7 empty] | TL | IC
|  | US1 to 5 - HTML | 8 | 3 | [7 empty] | IC | TL
|  | Unit tests | 5 | 2 | [7 empty] | DM
|  | SpringSecurity | 12 | 1 | Implementation | [6 empty] | DL | DM
[5 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday

## Sprint3 Week3
|  | Week 3 |  | Sprint 3 - Active Tickets
15
Effort Scale |  |  |  | 14 | [9 empty] | Team Members
Nº | Average time |  |  | 13 | [9 empty] | DM | Daniel Machado
1 | 1 hour |  |  | 12 | [9 empty] | DL | Daniel Lima
2 | 2 hours | Frontend Tests | 2 | 11 | [7 empty] | ALL |  | IC | Inês Clavel
3 | 4 hours | Domain Model | 5 | 10 | [7 empty] | IC |  | TL | Thales Lemos
5 | 1 day | Class Diagram | 5 | 9 | [7 empty] | ALL |  | ALL | All members
8 | 2 days | Report | 5 | 8 | [7 empty] | IC
12 | 3 days | US 5 Doc Update | 3 | 7 | [7 empty] | TL
|  | US 4 Doc Update | 3 | 6 | [7 empty] | IC
|  | US 3 Doc Update | 3 | 5 | [7 empty] | DL
|  | US 2 Doc Update | 3 | 4 | [7 empty] | DM
|  | US 1 Doc Update | 3 | 3 | [7 empty] | DL
|  | Frontend corrections | 3 | 2 | [7 empty] | TL | IC
|  | Unit tests | 8 | 1 | [7 empty] | ALL
[5 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday